## README
Diamond Event & Tent — Event Planning Template (2025)
How to use this template:
1) Start in Master Checklist: add your categories, tasks, owners, dates, and set Status. We provided example categories for you.
2) Track costs in Budget. Estimated Cost is auto-calculated. Totals/variance at bottom.
3) Manage vendors in Vendors (contacts, payments, etc.).
4) Use Permits to outline which permits you need and to track approvals.
5) Build your schedule in Event Schedule (time, activity name, owner, etc.)
6) Log any risks and mitigation strategies in Risk & Contingency. Note that risks can both opportunities and threats.
Tip: Upload this .xlsx to Google Drive and open with Google Sheets to collaborate.

## Master Checklist
Category | Task | Priority | Owners | Start Date | Due Date | Status | Prerequisites | Budgeted Cost (USD) | Actual Cost (USD) | Vendor / Supplier | Contact | Link | Notes
Goals | Define event purpose, audience, and success metrics (SMART goals) | High |  |  |  | Not Started
Budget | Create top-line budget (venue, F&B, rentals, AV, staff, marketing, contingency 10%) | High |  |  |  | Not Started
Date | Lock event date and backup weather date | Medium |  |  |  | Not Started
Guest List | Draft guest list and target headcount | Medium |  |  |  | Not Started
Venue | Shortlist venues; request proposals and walkthroughs | High |  |  |  | Not Started
Team | Assign planning roles and responsibilities | Medium |  |  |  | Not Started
Schedule | Draft event run-of-show with setup/strike timing | Medium |  |  |  | Not Started
Vendors | Source catering, rentals, AV, entertainment, photo/video | High |  |  |  | Not Started
Permits (Utah) | Review required permits (special event, noise, alcohol, food, mass gathering, DOT, tents/stages). See Permits tab. | High |  |  |  | Not Started
Marketing | Create promo plan (webpage, email, social, partners); open registrations | Medium |  |  |  | Not Started
Rentals & Logistics | Confirm tent/structure, power, flooring, heating/cooling, sanitation | High |  |  |  | Not Started
On-site | Staffing plan, signage, credentialing, check-in, security/first aid | Medium |  |  |  | Not Started
Post-Event | Debrief, surveys, reconcile budget, thank-yous, photo/video delivery | Medium |  |  |  | Not Started

## Budget
Category | Item | Quantity | Unit Cost (USD) | Estimated Cost (USD) | Actual Cost (USD) | Vendor | Website | Paid? | Notes
Decorations | Chairs | 4 | 1.85 | 7.4 | 7.4 | Diamond Event | https://diamondevent.com/rental-product/plastic-alloy-folding-chair-white/ | Yes
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Totals: | 7.4 | 7.4
|  |  | Variance (Actual - Est): |  | 0

## Vendors
Category | Vendor / Supplier Name | Service | Contact Name | Phone | Email | Website | Deposit Due | Balance Due | Notes
Food | Restaurant, Inc. | Catering | David Blake | 777-777-7777 | dblake@email.com | www.website.com | 500 | 1000

## Permits
Area | Permit Type | Requirement Summary | Lead Time (days) | Fee (USD) | Application Link | Contact | Status | Submitted Date | Approved Date | Notes
State (Utah) | Alcohol (Single Event) | Public event service of liquor requires DABS single event permit; venue may need license | 30 |  | https://abs.utah.gov/single-event-permit/ | DABS | Done | 2017-08-05 | 2017-09-15

## Event Schedule
Time | Activity | Description | Who Is Responsible | Location | Prerequisites | Notes
9:00 | Event Introduction | Event hosts announce events to participants and provide directions as needed. | Sarah Moore | Atrium | All participants must have properly checked in prior to this event. | Call event hosts if the check in process is expected to run late, this cannot run past 5 minutes of the planned start time.

## Risk & Contingency
Risk | Likelihood | Impact | Mitigation Plan | Owner | Status
Inclement Weather | Medium | Low | Move most activities indoors, provide warnings on social media | Marissa Kent | In Progress

## Contacts
Name | Role | Organization | Phone | Email | Notes
Jim Halloway | Facility Manager | Company, Inc. | 777-777-7777 | jhalloway@email.com | High importance, low communication need